## Stories
C-- | Group A4: Sarah Higgens, Michael Serino, Noah Moss, Xinyi Lyu, Zack Neefe
Story Number | Category | Title | Description | Acceptance Criteria | Criticality | Subtasks | Total Hours | Release # | Goal | Implemented | Notes | Who Wrote This
S.UI.01 | User Input | Add cars | As an admin, I need to add a new car to the database so that customers can know our current inventory. | 1. The car is added to the database. 2. The customer should be able to view the updated page from their end. | 5 | 1. Make a spike for a database design. (2 hrs) 2. Create database for our program. 5 3. Write the add functionailty. 1 | 8 | 1.1 | 4 | 100% |  | Sarah
S.UI.02 | User Input | Report an issue | As a registered user, I need to be able to report an issue with the vehicle so that I can get a replacement. | 1. The system has a page to report issues which are immediately sent to the place of rental. | 3 | 1. Create a new table in database 1 | 2 | 3.3 | 6 | 100% |  | Zack
S.UI.03 | User Input | Specify pick-up | As a registered user, I need to be able to decide where I pick-up the car so that my car rental fits my shcedule. | 1. The system has a page for date, time, and location for car pick-up. 2. The request is sent to the system admin | 5 | 1. Create GUI. 0.25 2. Write code in Rental Control. 1.25 3. Save information to database. 0.5 | 2 | 1.5 | 1 | 100% |  | Michael
S.UI.04 | User Input | Choose car components | As a registered user, I need to be able to specify exactly what components my rented car should have so that I can be sure I am driving the exact car that I want. | 1. The car that is selected has all of the components selected. | 4 | 1. Create a filter method in DBObject 1 2. Create a filter method in Vehicle Control 1 3. Add functionality to the GUI (already made) 1 | 3 | 2.5 | 3 | 100% | Components include: color, make, model, year, engine, and child protection (optional) | Noah
S.UI.05 | User Input | Delete cars | As an admin, I need to delete a car from the database because a certain car model may not be available. | 1. The car has to be completely removed from the database. | 5 | 1. Create a Delete in DB Object. .75 2. Call DBOject in Vehicle Control. 1.5 3. Update the database. .75 | 3 | 2.2 | 4 | 100% |  | Sarah
S.UI.06 | User Input | Report crashed car | As an admin, I need to be able to report that a car has been in an accident so that the car is not available in the database | 1. The car has been in an accident and the admin notifies the system. | 3 | 1. Create the gui to list all reported cars 1 | 2 | 3.2 | 6 | 100% |  | Michael
S.UI.07 | User Input | Purchase car | As a registered user, I need to be able to purchase the car I am renting so that I don't have to rely on renting vehicles any longer. | 1. The car is removed from the database 2. Transfer of ownership is noted | 2 | 1. Create GUI. 1 2. add methods for the user to purchase car. 1 | 2 | 3.4 | 1 | 100% |  | Noah
S.UI.08 | User Input | Making other admin accounts | As an admin, I need to be able to make other admin accounts because I may hire more managers. | 1. Only an admin must create other admin accounts. | 4 | 1. In User specfiy the create admin account in Cusomter Controler 1 | 1 | 2.6 | 2 | 100% |  | Sarah
S.UI.09 | User Input | Return car | As an admin, I need to verify if a car was returned otherwise all of the cars could get stolen. | 1. The system need to mark the returned cars as available. | 5 | 1. Write code in Rental Control. 0.25 2. Create Admin Interface. 0.25 3. Write code to sent Admin a notification 2 4. Save information to the database. 0.5 | 3 | 1.8 | 1 | 100% |  | Noah
S.UI.10 | User Input | Specify drop off location | As a registered user, I need to be able to choose a location to return the car so that I can get the closest location to me. | 1. There is a page for choosing the location of drop off with all locations selectable. | 5 | 1. Write code to save infomation to database. 1 | 1 | 1.6 | 1 | 100% | Drop off location does not necessarily need to be the same as pickup | Zack
S.UI.11 | User Input | Create a user account | As a unregistered user, I need to be able to create an account to become a registered user. | 1. There will be a sign up page. | 5 | 1. Create GUI. 0.25 2. Write code in customer control. 1.5 3. Save information to database. 0.25 | 2 | 1.2 | 1 | 100% |  | Sarah
S.UI.12 | User Input | Choose a car | As a registered user, I need to be able to choose a car so that I can rent the car. | 1.The system have a list of avaliable cars. 2. The system will change the selected car to be unavaliable. | 5 | 1. Create GUI. 0.25 2. Write code to search database. 1.75 | 1 | 1.3 | 3 | 100% |  | Xinyi
S.IO.01 | User Input and System Output | Modify cars | As an admin, I need to be able to modify an existing car in the database because some of the parameters for a given car could change. | 1. There needs to be an edit page. 2. The changes made to the car need to be saved into the database. | 4 | 1. Write tests for modify in DBObject 1 2. Write Modify in DBObject .5 3. Write Modify in Vehicle Control .25 4. Create GUI functionality .25 | 2 | 2.3 | 4 | 100% |  | Sarah
S.IO.03 | User Input and System Output | Blacklist | As an admin, I need to be able to place a registered user into a blacklist so that I can track what registered users are allowed to rent cars or not. | 1. The registered user will be placed on the blacklist. 2.The given user will not be able to rent a car if they tried. | 3 | 1. Create GUI. 2 2. Create method in admin control to update or blacklist user. 2 | 4 | 3.5 | 6 | 100% |  | Zack
S.IO.05 | User Input and System Output | Search Car Categories | As a registered user, I need to be able to search car categories so that I can find a specific kind of make/model type. | 1. The system will have a field to specify the search filter. | 4 | 1. Write method in DBObject to search. 2.5 2. Read from GUI and send to Vehicle Control. 1 3. Have Vehicle control talk between the two. 1.5 | 5 | 2.4 | 3 | 100% |  | Michael
S.SO.01 | System Output | Review the rental before committing | As a registered user, I need to see the order I am about to place before hitting the final submit button so that I can be sure there is no mistake in the order. | 1. When making a purchase, a confirmation page is shown before the final submit button. | 3 | 1. Display all info on the payment page 1 | 1 | 3.6 | 1 | 100% | Should apply for both rentals and purchases | Zack
S.SO.02 | System Output | Browse cars | As an unregistered user, I need to be able to browse for cars. | 1.There needs to be a few car type options to choose from. | 5 | 1. Create get all vehicles method in Vehicle Control .75 2. Design a basic GUI. .5 3. Create functionality on GUI. 1 | 4 | 2.1 | 1 | 100% |  | Xinyi
S.SO.04 | System Output | Track number of rental days | As an admin, I need to see how long the car has been rented for so that I can confirm the number of days the user has left to rent. | 1. The system will have a counter for how many days the customer has had the car. | 4 | 1. Write method in rental control. .25 2. Determine if it is overdue. .5 3. Display to Admin. .25 | 1 | 2.7 | 2 | 100% |  | Michael
S.SO.06 | System Output | Determine amount owed | As a registered user, I need to be able to view the rate for a rental I have made so that I know how much I need to pay. | 1. The system will calculate how much is owed. 2. Display this amount to the user. | 5 | 1. Calculate total from user input. 1 2. Display total to user. 1 | 2 | 1.7 | 1 | 100% |  | Noah
S.IO.02 | User Input and System Output | Pay for the rental | As a registered user, I need to be able to pay for the rental by cash or online so that I can finalize the payment. | 1. The user receives a confirmation page. | 5 | 1. Create GUI. 0.5 2. Check to see if customer's info is vaild. 3.5 | 4 | 1.4 | 1 | 90% |  | Xinyi
S.SO.03 | System Output | Apply fees | As an admin, I need to be able to apply additional fees to customer accounts so that customers who have trashed a car will give us money. | 1. The system has a page to apply fees to specific purchases. 2. Only accessible by admins. | 3 | 1. Create methods that check rental for fees 1 | 2 | 3.1 | 6 | 80% | Fineable offenses are things like leaving a significant mess in the car or crashing without insurance. | Zack
S.IO.04 | User Input and System Output | Review customers credit | As an admin, I need to be able to review a customer's credit so that I can determine if the customer eligible to rent. | 1. There will be a way from the admin to enter the customer's card information to see their credit score. | 2 |  | 1 | 3.7 | 2 | 0% |  | Xinyi
S.SO.05 | System Output | Calendar view | As an admin, I need to be able to view a calendar because I want to see how many cars I am loaning in one day. | 1. The admin needs to have the ability to select a future day from a calendar to look at the cars that will be rented out. | 1 | Create the GUI (may take long) 7 | 7 | 3.8 | 2 | 0% | Will be pushed back due to time constraints. | Sarah

## Goals
Goal Number | Key Goal | Keyword
1 | Rent a car | Rent
2 | Admin duties | Administrative
3 | Select a car | Select
4 | Maintain Inventory | Inventory
5 | Review car selection | Review
6 | Report cars and users | Report